## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
PB-01 | User Registration | As a TA, I want to register an account so that I can access the system. | Must | Sprint 1 | 1. TA can register with valid email and password 2. system validates input 3. confirmation shown. | 3 | Core recruitment workflow | 2026-03-23 | 2026-04-05
PB-02 | User Login | As a user, I want to login so that I can access my account. | Must | Sprint 1 | 1. User can login with valid credentials 2. error shown for invalid login. | 2 | Core recruitment workflow | 2026-03-23 | 2026-04-05
PB-03 | Create Profile | As a TA, I want to create my profile so that I can apply for jobs. | Must | Sprint 1 | 1. TA can input personal info 2. upload CV 3. system stores profile. | 5 | Core recruitment workflow | 2026-03-23 | 2026-04-05
PB-04 | Upload CV | As a TA, I want to upload my CV so that my qualifications are recorded. | Must | Sprint 1 | 1. CV can be uploaded in PDF format 2. validation on size/type 3. stored correctly. | 3 | Core recruitment workflow | 2026-03-23 | 2026-04-05
PB-05 | Browse Jobs | As a TA, I want to browse job listings so that I can find suitable positions. | Must | Sprint 1 | 1. Only approved jobs visible 2. title, module, deadline shown 3. expired jobs hidden 4. TA can view details. | 5 | Core recruitment workflow | 2026-03-23 | 2026-04-05
PB-06 | Post Job | As a MO, I want to post a job so that TAs can apply. | Must | Sprint 1 | 1. Lecturer can create job with title, module, deadline, workload 2. saved correctly 3. status 'pending review'. | 5 | Core recruitment workflow | 2026-03-23 | 2026-04-05
PB-07 | Admin Review Profile | As an admin, I want to review TA profiles so that only qualified TAs are approved. | Must | Sprint 1 | 1. Admin can approve/reject 2. TA notified 3. feedback stored. | 3 | Approval and governance workflow | 2026-03-23 | 2026-04-05
PB-08 | Admin Review Job | As an admin, I want to review job posts so that only valid jobs are published. | Must | Sprint 1 | 1. Admin can approve/reject jobs 2. feedback stored 3. status updated. | 3 | Approval and governance workflow | 2026-03-23 | 2026-04-05
PB-09 | Define Data Storage Format | As a developer, I want to define the file storage format so that system data is stored consistently. | Could | Sprint 1 | 1. System uses JSON or CSV format for data storage. 2. User data is stored in files. 3. Job data is stored in files. 4. Application data is stored in files. | 2 | Technical architecture constraint | 2026-03-23 | 2026-04-05
PB-10 | File Data Persistence | As a developer, I want to store system data in JSON/CSV so that the system works without DB. | Must | Sprint 1 | 1. User, job, application data stored in files 2. loaded on restart. | 5 | Addresses coursework file‑storage constraint | 2026-03-23 | 2026-04-05
PB-11 | Apply Job | As a TA, I want to apply for a job so that I can get a position. | Must | Sprint 2 | 1. TA can submit application 2. system records timestamp 3. status 'pending'. | 5 | Core recruitment workflow | 2026-04-06 | 2026-04-19
PB-12 | Review Applicants | As a lecturer, I want to review applicants so that I can shortlist TAs. | Must | Sprint 2 | 1. Lecturer can accept/reject applicants 2. TA notified 3. feedback stored. | 5 | Core recruitment workflow | 2026-04-06 | 2026-04-19
PB-13 | Application Status | As a TA, I want to view application status so that I can track progress. | Must | Sprint 2 | 1. Statuses: pending, shortlisted, accepted, rejected, withdrawn 2. dashboard shows updates. | 3 | Core recruitment workflow | 2026-04-06 | 2026-04-19
PB-14 | Edit Profile After Rejection | As a TA, I want to edit and resubmit my profile after rejection so that I can correct mistakes. | Should | Sprint 2 | 1. TA views feedback 2. edits profile 3. resubmits 4. timestamp recorded. | 3 | Supports rejection and resubmission flow | 2026-04-06 | 2026-04-19
PB-15 | Edit Job Post After Rejection | As a lecturer, I want to revise rejected job posts so that I can meet approval. | Should | Sprint 2 | 1. Lecturer sees rejection reason 2. edits 3. resubmits 4. status 'pending'. | 3 | Supports rejection and resubmission flow | 2026-04-06 | 2026-04-19
PB-16 | Withdraw Application | As a TA, I want to withdraw application before deadline so that I can change decision. | Should | Sprint 2 | 1. TA can withdraw 2. status updated to 'withdrawn' 3. lecturer notified. | 2 | Exception handling workflow | 2026-04-06 | 2026-04-19
PB-17 | Search and Filter Jobs | As a TA, I want to search and filter jobs so that I can quickly find positions. | Should | Sprint 2 | 1. Search by module 2. filter by deadline/workload 3. results update dynamically. | 3 | Usability support feature | 2026-04-06 | 2026-04-19
PB-18 | View Application History | As a TA, I want to view my past applications so that I can track job history. | Should | Sprint 2 | 1. TA sees all submitted applications with status, title, module, date. | 3 | User tracking support feature | 2026-04-06 | 2026-04-19
PB-19 | Notification | As a user, I want to receive notifications so that I know system updates. | Should | Sprint 3 | 1. TA notified of application status changes 2. Lecturer notified of submissions 3. Admin notified of approvals. | 2 | Process communication feature | 2026-04-20 | 2026-05-05
PB-20 | Monitor Workload | As an admin, I want to monitor TA workload so that assignments are balanced. | Must | Sprint 3 | 1. Weekly hours calculated 2. overloaded TAs highlighted 3. summary dashboard shown. | 3 | Administrative monitoring feature | 2026-04-20 | 2026-05-05
PB-21 | Export Reports | As an admin, I want to export workload reports so that I can analyze TA allocation. | Could | Sprint 3 | 1. Admin exports CSV including TA, modules, workload summary. | 3 | Administrative reporting feature | 2026-04-20 | 2026-05-05
PB-22 | System Logs / Audit | As an admin, I want to view system activity logs so that I can monitor usage. | Could | Sprint 3 | 1. Logs include login, job posting, applications 2. admin can view. | 3 | Administrative monitoring feature | 2026-04-20 | 2026-05-05
PB-23 | Basic System Security | As an admin, I want basic system security controls so that user data is protected. | Should | Sprint 3 | 1. Passwords are stored securely. 2. Unauthorized users cannot access admin pages. 3. User sessions are validated. 4. System prevents unauthorized actions. | 3 | Security non‑functional requirement | 2026-04-20 | 2026-05-05
PB-24 | System Performance | As a user, I want the system to respond quickly so that I can use it efficiently. | Should | Sprint 3 | 1. Job list loads within acceptable time. 2. Application submission completes successfully. 3. System handles multiple users without crash. 4. System maintains stable response time. | 3 | Performance non‑functional requirement | 2026-04-20 | 2026-05-05
PB-25 | Data Backup | As an admin, I want system data backed up so that info won't lost. | Could | Sprint 3 | 1. System creates backups 2. admin can restore 3. includes all data. | 3 | System reliability feature | 2026-04-20 | 2026-05-05
PB-26 | AI Job Matching | As a TA, I want AI to recommend jobs so that I can apply efficiently. | Could | Sprint 4 | 1. System suggests suitable jobs based on profile 2. TA can see recommendations. | 5 | AI enhancement feature | To Be Determined | To Be Determined
PB-27 | Notifications Customization | As a user, I want to configure notifications so that I can receive relevant updates. | Could | Sprint 4 | 1. User can enable/disable notification types 2. changes saved. | 2 | User preference enhancement | To Be Determined | To Be Determined
PB-28 | Admin Configuration | As an admin, I want to configure system parameters so that rules can be adjusted. | Could | Sprint 4 | 1. Admin can set thresholds 2. save config 3. changes affect system behavior. | 3 | Technical support feature | To Be Determined | To Be Determined
PB-29 | Reports Scheduling | As an admin, I want to schedule automatic report generation so that I get timely summaries. | Could | Sprint 4 | 1. Admin sets schedule 2. system generates reports automatically. | 3 | Automation enhancement feature | To Be Determined | To Be Determined
PB-30 | Error Handling & Alerts | As a user, I want clear error messages and alerts so that I can correct issues. | Should | Sprint 4 | 1. System shows meaningful error messages 2. alerts on failure 3. logs created. | 3 | System reliability feature | To Be Determined | To Be Determined
PB-31 | AI Workload Balancing | As an admin, I want the system to suggest balanced TA allocations so that workloads are evenly distributed. | Could | Sprint 4 | To Do | 5 | AI workload optimisation feature | To Be Determined | To Be Determined
PB-32 | Identify Missing Skills | As a TA, I want the system to identify missing skills in my profile so that I can improve my qualifications for future job applications. | Could | Sprint 4 | 1. System analyses TA profile and job requirements. 2. System identifies missing skills for specific jobs. 3. System displays suggested skills to improve. 4. TA can view suggestions in dashboard. | 5 | AI skill‑gap analysis feature | To Be Determined | To Be Determined